COMPUTING Action Plan	Year 2023/24

| Priority: Heamoor School is to be compliant with National Curriculum objectives |  |  |  |  |  |  | leader: Scott Markham |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TargetS: A. The implementation of a new computing scheme and that all staff a re confident in its delivery B. All stakeholders are aware of the intent, implementation and impact that is used to ensure that al children are digitally literate by the end of Key Stage 2 C. Computing is given an appropriate level of importance within the foundation curriculum |  |  |  |  |  |  |  |  |  |  |  |  |
| Key aspects: t |  |  |  |  |  |  |  |  |  |  |  |  |
| Success criteria | Action(s) to be taken | Who is responsible? | Who is involved? | Start/ finish dates | Resources: Time, copying, class assistant etc. |  | Monitoring of implementation |  |  | Evaluation against success criteria |  |  |
| A Success is: Children will progress through the National Curriculum Computing objectives and will develop a deep understanding within each year group as part of the school curriculum their understanding and application of skills- evident in Project books and digital storage. | New Computing Scheme to be implemented (we no longer subscribe to Purple Mash SM researched available schemes and in consultation with JF, decided on NCCE scheme. The scheme was launched via a staff meeting in October 23 Microbits to be resourced and added to the school curriculum offer | SM SM | SM/SLT SM | 23/24 academic Year 23/24 academic year | NCCE-(login required for all staff Subject release time for SM Microbits to be ordered via link | Cost/ source Nil cost for NCCE Nil cost for microbits | How? Via teaching Questionnaire Pupil conferencing Project ‘book look’ | Who? SM/all teachers SM/pupils All staff | When? Dec 23 Dec 23 Dec 23 | How? | Who? | When? |
| B Success is: all stakeholders are aware of the Computing values and rationale behind the consistent implementation of the school curriculum. Teaching staff will be confident when planning appropriate learning opportunities | 3is document to be drafted Long Term Plan to be accessible by all staff | SM SM | SM/SLT SM/SLT | 23/24 academic Year 23/24 academic Year | Subject release time for SM Subject release time for SM | Nil cost Nil cost | Monitoring of MTP for all classes Monitoring of MTP for all classes | SM/SLT SM/SLT | Jan 24 Jan 24 |  |  |  |
| C Success is: Computing is valued and given appropriate importance within the school curriculum | Website to be updated Regular exposure is to be given via the school newsletter | SM SM | SM/all teachers SM/all teachers | 23/24 academic Year 23/24 academic Year | Subject release time for SM Subject release time for SM | Nil cost Nil cost | Regular updates and check of website Termly sample of newsletter | SM SM | Termly Termly |  |  |  |
|  |  |  |  |  |  | Total: |  |  |  |  |  |  |
| Overall evaluation of progress: Further action required: |  |  |  |  |  |  |  |  |  |  |  |  |

C  EAIS Cornwall Education Advisory and Improvement service